## Overview & Summary
🌟 UDAI WEB APPLICATION & CLINICAL ECOSYSTEM
Comprehensive End-to-End Project Development & Delivery Summary
📌 SYSTEM ARCHITECTURE & TECH STACK
Frontend Portal | React, Vite, Vanilla CSS, Lucide Icons | Public website, Appointment booking UI, Donations, Team | Active / Verified
Admin Panel | React, Vite, Real-time Dashboard, SSE | WhatsApp Appointments, Live Messages, Availability Manager | Active / Verified
Backend API (Port 4000) | Node.js, Express, TypeScript | MSG91 WhatsApp Bot APIs, Payment Webhook, Booking Engine | Active / Verified
Admin Backend (Port 5003) | Node.js, Express, MongoDB Native | Admin Authentication, Dynamic Availability, Data Sync | Active / Verified
Database | MongoDB Atlas (Database: 'udai') | Collections: appointments, availabilities, webhookmessages, etc. | Active / Verified
Messaging & Payment | MSG91 In-Chat WhatsApp & Razorpay | Automated booking flows, dynamic slot calculation, payments | Active / Verified
Module / Area | Key Accomplishments
MSG91 WhatsApp Booking Engine | Dynamic date/slot resolution, 45-min interval generation, instant persistence to MongoDB 'udai' |  | 100% Operational
MSG91 Payment Webhook | In-Chat WhatsApp Payment confirmation, auto status change to 'completed' / 'confirmed' |  | 100% Operational
First Session Service Guard | Auto-assignment to Counselling for new patients without DB migrations or flow changes |  | 100% Operational
Dynamic Availability Management | MongoDB 'availabilities' collection, Admin UI live toggle, instant Bot date/slot sync |  | 100% Operational
Clinical Working Hours & Slot Math | Custom shifts & lunch exclusion (Atal, Sakshi, Harsimran, Standard) across all 7 departments |  | 100% Operational
Anti-Collision Slot Locking | Therapist-level slot capacity checking, zero-capacity omission, double-booking rejection |  | 100% Operational
Balanced Alternating Assignment | Round-robin load balancing across multi-doctor departments (Speech, OT, Counselling, etc.) |  | 100% Operational
Admin Panel UI & Action Menus | Merged Child+Parent layout, [New]/[Returning] badges, 3-dots action menu with WhatsApp chat |  | 100% Operational
Website UI/UX & Team Sync | Live MongoDB team sync, impact donation flow, responsive 5+4 affiliations, team gallery |  | 100% Operational

## Today's Detailed Work Log
TODAY'S WORK EXECUTION & DELIVERY LOG (2026-09-02)
# | Category | Feature / Fix Name | Affected Files & Endpoints | Technical Implementation Summary | Verification
1 | Payment Webhook | MSG91 WhatsApp Payment Webhook Handler | backend/src/controllers/msg91PaymentWebhookController.ts backend/src/routes/msg91PaymentWebhook.ts backend/src/app.ts POST /api/msg91/payment-webhook | Implemented webhook parser to catch MSG91 in-chat payment events. Queries latest pending appointment by phone in MongoDB Atlas 'udai', updates paymentStatus to 'completed', bookingStatus to 'confirmed', transactionId, and returns status 200 { success: true }. | Verified (cURL 200 OK)
2 | Admin Panel | WhatsApp Messages Table & 3-Dots Menu Redesign | admin-main/frontend/src/components/WhatsAppMessagesPage.jsx backend/src/routes/webhook.ts admin-main/backend/src/routes/admin.js | Redesigned messages table: combined Child & Parent in single cell with subtitle, added [New]/[Returning] badges, added 'Service/Concern' column, cleaned 'Paid' badge logic, and built full 3-dots action menu (View Details, Mark as Paid, Reschedule, wa.me direct chat, Cancel). | Verified in UI
3 | Booking Engine | Ultra-Flexible MSG91 Booking Endpoint | backend/src/services/msg91AppointmentService.ts backend/src/routes/msg91Booking.ts POST /api/msg91-booking | Replaced strict Zod validation with resilient multi-key payload extraction (patientName, phone, date, time, concern, etc.). Explicitly connected MongoDB to 'udai' database. Synced bookings across 'appointments', 'webhookmessages', and 'chatbotsubmissions'. | Verified (cURL 200 OK)
4 | Guard Logic | First Session Service Guard | backend/src/services/msg91AppointmentService.ts admin-main/frontend/src/components/WhatsAppMessagesPage.jsx | Normalized phone variants and queried appointments collection count. If 0 (New Patient): forced department to 'Counselling', set isFirstSession = true, and appended auto-assigned note. If > 0 (Returning Patient): preserved selected service and set isFirstSession = false. Zero DB migration needed. | Verified (cURL Test)
5 | Availability | Dynamic Database-Backed Availability Collection | backend/src/models/Availability.ts backend/src/routes/availability.ts admin-main/backend/src/routes/admin.js GET & POST /api/availability | Created MongoDB 'availabilities' collection with compound unique index { therapistName: 1, date: 1 }. Built GET /api/availability date-range query and POST /api/availability/toggle upsert handler across both backends. | Verified (cURL + MongoDB)
6 | Admin Panel | Availability Manager Real-Time Dashboard | admin-main/frontend/src/components/AvailabilityManagerPage.jsx admin-main/frontend/src/services/adminApi.js admin-main/frontend/src/App.jsx | Built dedicated Availability Manager UI with 5-day rolling window, department filter pills, total slot metrics, and 1-click state toggling (Green = Available, Red = Not Available) with optimistic UI updates, auto-poll sync, and toast notifications. | Verified in UI
7 | WhatsApp Bot | Dynamic Availability Bot Hook | backend/src/services/bookingService.ts backend/src/services/msg91AppointmentService.ts | Hooked availabilities collection directly into WhatsApp booking endpoints: GET /api/msg91-booking/dates automatically removes dates where all department doctors are marked off; GET /api/msg91-booking/slots filters capacity accordingly. | Verified (cURL Test)
8 | Clinical Shift | Shift Working Hours & 45-Min Slot Math | backend/src/services/bookingService.ts backend/src/models/Therapist.ts | Implemented strict 45-minute interval slot math for all clinic rosters: Atal (09:15-17:15, lunch 13:00-13:30), Sakshi (10:00-14:00, no lunch), Harsimran (13:00-17:15, no lunch), and Standard shift (10:00-16:30, lunch 13:00-13:30). Strictly excluded lunch overlap. | Verified (cURL Slots)
9 | Admin UI | Shift Timing Badges in Availability Table | admin-main/frontend/src/components/AvailabilityManagerPage.jsx | Rendered clear shift window badges (e.g. '🕒 09:15 - 17:15 (Lunch: 1:00-1:30)') under each doctor's name and designation badge in the first column of the Availability Manager. | Verified in UI
10 | Bug Fix | Therapist-Level Anti-Collision & Slot Locking | backend/src/services/bookingService.ts backend/src/services/msg91AppointmentService.ts | Prevented double-booking and slot collision: slot generator queries active bookings in 'appointments' collection, omits 0-capacity slots from WhatsApp bot list, and assignTherapist strictly returns null on collision, rejecting duplicate attempts. | Verified (Tested Collisions)
11 | Bug Fix | Robust Department Payload Normalization | backend/src/services/msg91AppointmentService.ts backend/src/services/bookingService.ts | Exhaustively extracts department from concern_of_child, service, selected_service, service_concern, etc., and normalizes strictly across all 7 departments (Speech Therapy, Physiotherapy, Special Educator, Physical Therapy, Academic Support, Counselling, OT). | Verified (cURL Test)
12 | Load Balancing | Balanced Alternating (Round-Robin) Assignment | backend/src/services/bookingService.ts backend/src/services/msg91AppointmentService.ts | Implemented multi-doctor load balancing: counts active bookings assigned to eligible free doctors today in appointments collection and assigns the doctor with the lowest count, alternating bookings evenly one-by-one. | Verified (Alternating Test)

## All Project Work & Change Log
COMPLETE UDAI PROJECT MASTER WORK & COMMIT LOG
# | Subsystem | Feature / Work Item | Description & Implementation Scope | Branch / Target | Status
1 | WhatsApp Engine | Multi-Therapist Balanced Alternating Assignment | Even round-robin assignment across eligible clinic doctors based on active appointment count today. | main (backend) | Completed
2 | WhatsApp Engine | Anti-Collision & Double-Booking Lock | Real-time appointment capacity checking, zero-capacity slot omission, strict duplicate rejection. | main (backend) | Completed
3 | WhatsApp Engine | Clinical Working Shift Hours Math | 45-minute interval generator respecting Atal, Sakshi, Harsimran, Standard shifts and lunch breaks. | main (backend) | Completed
4 | Admin Panel | Shift Hours Display Badges | Rendered exact doctor shift window and lunch timings inside the Availability Manager table. | main (admin) | Completed
5 | Admin Panel | Dynamic Database Availability Manager UI | Real-time 5-day doctor availability manager with 1-click toggling, department filtering, and auto-sync. | main (admin) | Completed
6 | Database / API | MongoDB 'availabilities' Collection & Endpoints | Unique compound index { therapistName: 1, date: 1 }, GET /api/availability, POST /api/availability/toggle. | main (backend) | Completed
7 | Guard Logic | First Session Guard (Auto-Counselling) | Queries appointments collection count by phone; auto-assigns new users to Counselling with visual badges. | main (backend) | Completed
8 | Admin Panel | WhatsApp Messages Table & Action Menu Redesign | Combined Child+Parent cell, [New]/[Returning] badges, Service column, clean Paid logic, 3-dots action menu. | main (admin) | Completed
9 | Webhook / Pay | MSG91 In-Chat Payment Webhook Handler | Mounted POST /api/msg91/payment-webhook; auto-completes appointments on WhatsApp payment event. | main (backend) | Completed
10 | Booking API | Resilient MSG91 Booking Endpoint | Ultra-flexible field parsing for customerNumber, childName, date, time; persists to MongoDB 'udai'. | main (backend) | Completed
11 | Frontend Portal | Dynamic Team Sync to Website | Connected 'Meet Our Team' section to live MongoDB therapist database; synced photos and roles. | main (frontend) | Completed
12 | Donations | Custom & Choose Your Impact Donation Flow | Configured donation amounts, unified button handlers, connected Razorpay payment checkout. | main (frontend) | Completed
13 | Frontend Portal | Affiliations & About Collage Layout Fix | Structured 5+4 responsive affiliation grid alignment, full uncropped photo rendering, certification cards. | main (frontend) | Completed
14 | Security & CORS | Cross-Origin & Reverse Proxy Configuration | Added production domain https://udaiapi.datamoshtechnologies.com, pms domain, and dev ports to CORS. | main (backend) | Completed
15 | Admin Backend | Data Synchronization Across Collections | Synchronized updates across 'appointments', 'webhookmessages', and 'chatbotsubmissions'. | main (admin) | Completed
16 | Frontend Build | Router ErrorBoundary & Base Asset URL Fix | Fixed Vite base URL '/' to eliminate MIME type script loading errors on deployment. | main (frontend) | Completed
17 | Git Management | Safe Branch Merge & Shubham-Update Isolation | Merged final-updates and main while strictly isolating and preserving shubham-update untouched. | main (git) | Completed

## Clinical Roster & Shifts
UDAI CLINIC DEPARTMENT ROSTER & WORKING SHIFT MATRIX
# | Department | Doctor / Therapist | Designation | Working Shift | Lunch Window | Slot Duration & Rules
1 | Speech Therapy | Mr. Atal | Speech Therapist | 09:15 - 17:15 | 13:00 - 13:30 (30 min) | 45 min (09:15 to 16:30)
2 | Speech Therapy | Dr. Sakshi | Speech Therapist | 10:00 - 14:00 | No Lunch Break | 45 min (10:00 to 13:00)
3 | Physiotherapy | Dr. Divya | Physiotherapist | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
4 | Special Educator | Ms. Sobha | Special Educator | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
5 | Special Educator | Ms. Sonia | Special Educator | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
6 | Special Educator | Ms. Ranjana | Special Educator | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
7 | Physical Therapy | Dr. Durgesh | Physical Therapist | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
8 | Academic Support | Ms. Sonia | Academic Instructor | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
9 | Academic Support | Ms. Sobha | Academic Instructor | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
10 | Counselling | Ms. Tanu | Psychological Counsellor | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
11 | Counselling | Ms. Sonia | Counsellor | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
12 | OT | Ms. Nikki | Occupational Therapist | 10:00 - 16:30 | 13:00 - 13:30 (30 min) | 45 min (10:00 to 15:45)
13 | OT | Ms. Harsimran | Occupational Therapist | 13:00 - 17:15 | No Lunch Break | 45 min (13:00 to 16:30)

## API Endpoints Reference
UDAI BACKEND & ADMIN API ENDPOINTS REFERENCE
# | Method | API Endpoint | Target Service | Request Payload / Query Params | Response Output Contract
1 | POST | /api/msg91/payment-webhook | Payment Webhook Controller | { phone/customer_mobile, transaction_id, status } | { success: true, message: 'Payment webhook processed' }
2 | GET | /api/msg91-booking/dates | WhatsApp Bot Booking Engine | ?department=Speech%20Therapy | { success: true, data: [{ title, value }] } (5 days, excludes 0-slot dates)
3 | GET | /api/msg91-booking/slots | WhatsApp Bot Booking Engine | ?department=Speech%20Therapy&date=2026-09-03 | { success: true, data: [{ title, value, time, isAvailable, availableCount }] }
4 | POST | /api/msg91-booking | WhatsApp Bot Booking Engine | { customerNumber, childName, department, appointment_date, appointment_time } | { success: true, data: AppointmentRecord, message: 'Booking saved' }
5 | GET | /api/availability | Availability Manager API | ?startDate=2026-09-02&endDate=2026-09-06 | { success: true, count, data: IAvailability[], configuredTherapists }
6 | POST | /api/availability/toggle | Availability Manager API | { therapistName, department, date, isAvailable } | { success: true, data: IAvailability, message: 'Availability updated' }
7 | PATCH | /api/webhook/messages/:id | Admin Live Messages & Sync | { status, paymentStatus, appointmentDate, appointmentTime, assignedTherapist } | { success: true, data: WebhookMessage } (Syncs across 3 collections)
8 | GET | /api/admin/bootstrap | Admin Portal Bootstrap | Header: Authorization Bearer Token | { success: true, data: { user, therapists, products, stats } }
9 | GET | /api/therapists/unavailability | Therapist Leaves Management | None | { success: true, data: ITherapistUnavailability[] }